## Defect Tracker
Authentication Module - QA Bug Report Tracker
Generated: May 20, 2026 ¦ Cycle: Alpha Sprint 1
Bug ID | Test Case ID | Module | Summary | Description | Expected Result | Actual Result | Severity | Priority | Status | Environment | Reporter
BUG-AUTH-001 | TC-AUTH-010 | Login | Password characters briefly visible in plain text during masking | 1. Navigate to Login URL. 2. Enter text in the password field. Observe: The characters remain visible as plain text for a split second before transforming into dots/asterisks, exposing sensitive data to shoulder surfing. | Password field input must be masked immediately upon entry without displaying plain text. | Password characters are briefly visible in plain text before masking. | Medium | High | New | QA Staging | QA Automation Engineer
BUG-AUTH-002 | TC-AUTH-015 | Signup | Signup form accepts invalid mobile number format without validation error | 1. Open Signup page. 2. Input an invalid or arbitrary length mobile number (e.g., '1234abc'). 3. Click Submit. | The system should trigger a validation error 'Invalid mobile number format' and block form submission. | Mobile number accepted without any validation error, and the request was allowed and submitted to the backend. | High | High | New | QA Staging | QA Automation Engineer